## Slide 1
PetroNusa
Strategic Transformation of Fuel Retail
and Adjacent Businesses
Statement of Work
Prepared for the PetroNusa Strategy Committee
Aurelian & Co.

## Slide 2
Contents
1
Why fuel retail, why now
2
PetroNusa today — what we heard
3
Our understanding of the brief: Strategic Goals and Objectives
4
Proposed engagement approach
5
Phasing, timeline and governance
6
Deliverables and standard examples
7
Team and expert bench
8
Next steps
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
2 / 21

## Slide 3
Executive summary
An 18-month, three-phase transformation engagement against five RFP Objectives, anchored in PetroNusa's three Strategic Goals, governed through seven Steering Committees, delivered by a senior team supported by a fuel retail expert bench.
Scope
Five Objectives — Fuel Retail Competitive Position, Non-Fuel Retail Build, Dealer and Estate Operating Model, Payments and Loyalty, and an integrated Transformation Roadmap.
Shape
Three phases — Diagnostics (~3 months), Strategy (~5 months), Implementation support (~10 months).
Governance
Seven Steering Committees, weighted toward direction-setting in Phases 1 and 2.
Team
Aurelian senior team on the ground in Sariwon, supported by a curated expert bench across fuel retail, non-fuel retail, payments and operating model.
Outcome
A defended core fuel retail position, a credible non-fuel retail second leg, a modernised operating model, and a unified customer wallet.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
3 / 21

## Slide 4
Why fuel retail, why now
Three forces are reshaping fuel retail across Asian emerging economies — and the window to move first within Sariwon is narrowing.
1
The pump is no longer the only product
Measured the way regional peers report it, non-fuel is ~26% of their gross profit against ~8% at PetroNusa — an eighteen-point gap. On a revenue basis both sit in single digits: peers at 6–8%, PetroNusa at 3%. The competitive winners in the next five years will be those that build the non-fuel proposition while volumes are still strong enough to fund the investment.
2
Customers expect a wallet, not a card
Across regional markets, integrated mobile wallets covering fuel, convenience, food, and parking are now the entry-level customer experience. ArthaFuel and KhatuFuel are already there. PetroNusa is not.
3
The dealer model is overdue a reset
Across the region, operators are revisiting commission structures, technology integration, and performance management of the dealer estate. The retailers who modernise now will have the dealer base ready when EV-driven volume decline becomes material in the late 2020s.
For an operator of PetroNusa's scale and position, the cost of moving in the next twelve months is far below the cost of moving in three years.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
4 / 21

## Slide 5
PetroNusa today — what we heard
A market-leading network facing simultaneous pressure from share loss, an underbuilt non-fuel proposition, and an operating model that has not kept pace with the competition.
Scale and position
620 stations across Sariwon
34% national market share by volume
Largest network in the country
40% sovereign ownership through the Investment Authority
Margin pressure
Group EBITDA margin down 2.21pp in a single year
From 8.40% in FY2023 to 6.19% in FY2024
Compression driven principally by fuel retail
Non-fuel margins flat at small contribution
Share loss to challengers
ArthaFuel (21% share) and KhatuFuel (18% share)
~4 percentage points gained combined over three years
Principally at PetroNusa's expense
Both moved earlier on non-fuel and payments
Underbuilt non-fuel proposition
NFR at ~8% of Group gross profit; ~3% of Group revenue
Versus ~26% of gross profit at comparable regional peers
Convenience at ~95 stations
Food-service at ~30; car wash at ~140 — limited and inconsistent
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
5 / 21

## Slide 6
Our understanding of the brief: Strategic Goals
The engagement is commissioned in service of three Strategic Goals defined by PetroNusa.
Strategic Goal 1
Defend and selectively grow PetroNusa's market position in core fuel retail across the Sariwon network through targeted pricing, format, and operational improvements.
Strategic Goal 2
Build a material non-fuel retail business at the station, contributing meaningfully to Group revenue and gross profit within the engagement horizon.
Strategic Goal 3
Modernise the operating model across the dealer and company-operated estate, including governance, performance management, and technology enablement, to support the future shape of the business.
Wording reflects PetroNusa's RFP verbatim — these statements anchor the engagement scope and remain unchanged in our proposal.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
6 / 21

## Slide 7
Our understanding of the brief: Objectives
Five Objectives across the engagement, each tied to one or more Strategic Goal.
Objective | Verbatim text from the RFP | Serves
A — Fuel Retail Competitive Position | Diagnose the drivers of PetroNusa's share loss at the pump over the last three years and develop a competitive response plan covering pricing architecture, site format, customer proposition, and network footprint decisions, in service of Strategic Goal 1. | SG1
B — Non-Fuel Retail Build | Define the target non-fuel retail proposition for PetroNusa, sized and sequenced by station archetype, including category mix, partnership versus own-build choices, and the supporting operating capability required, in service of Strategic Goal 2. | SG2
C — Dealer and Estate Operating Model | Review the current operating model across the company-operated and dealer-operated estate, identify gaps in governance, performance management, and technology, and propose a revised operating model with a phased path to implementation, in service of Strategic Goal 3. | SG3
D — Payments and Loyalty | Assess PetroNusa's current payments infrastructure and loyalty proposition, benchmark against domestic and regional best practice, and recommend a path to a unified customer wallet and loyalty programme that supports both fuel and non-fuel propositions, in service of Strategic Goals 1 and 2. | SG1, SG2
E — Transformation Roadmap and Programme Set-up | Synthesise the recommendations across Objectives A–D into a single integrated transformation roadmap, define the implementation governance, and stand up the programme infrastructure required to execute, in service of all three Strategic Goals. | SG1, SG2, SG3
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
7 / 21

## Slide 8
Proposed engagement approach
A three-phase approach — Diagnostics, Strategy, Implementation. All five Objectives are in scope throughout; the depth is weighted to Objectives A and D, where the near-term earnings move, with Objective B sequenced behind the station-archetype fact base.
Objective | Diagnostics (~3 months) | Strategy (~5 months) | Implementation (~10 months)
A — Fuel Retail Competitive | Share-loss diagnostic, pricing audit, site performance review | Competitive response plan, network footprint decisions | Pilot pricing architecture, format upgrades on 50–80 sites
B — Non-Fuel Retail Build | Category opportunity sizing, station archetype review | Target proposition by archetype, partnership decisions | Pilot launch at 30 sites; scale playbook
C — Operating Model | Current-state operating model review; gap analysis | Target operating model design with phased transition | Operating model rollout — governance, performance management, technology
D — Payments and Loyalty | Current-state payments and loyalty assessment; regional benchmark | Unified wallet design and loyalty proposition | Wallet build oversight, launch readiness
E — Roadmap & Programme | Integration framework | Integrated transformation roadmap; governance design | Programme management infrastructure stood up
All five Objectives run through all three phases, but not at equal depth: A and D carry Phases 1 and 2, B builds from the Phase 1 fact base to a Phase 3 pilot, and C is paced against the dealer agreement calendar. Phase entry and exit criteria are defined per Objective.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
8 / 21

## Slide 9
Phase 1: Diagnostics
Anchor every recommendation in a clear-eyed view of where PetroNusa stands and why.
Approx. 3 months
Phase objectives
Independent fact base across all five Objective areas
Validated diagnosis of share loss, NFR gap, operating model gaps, payments/loyalty gap
Aligned framing of the strategic choices to be made in Phase 2
Key activities by Objective
Objective A: share-loss waterfall, pricing audit, site performance review
Objective B: category opportunity sizing, station archetype clustering
Objective C: current-state operating model review, gap analysis
Objective D: payments and loyalty current-state and regional benchmark
Objective E: integration framework for cross-Objective findings
Phase deliverable
Diagnostics Synthesis Deck with appendices covering each Objective area, presented at SC3.
Audience: PetroNusa Strategy Committee, CEO, CFO.
Entry criteria
Project kick-off completed (SC1); data access agreed.
Exit criteria
SC3 sign-off of diagnostic findings and Phase 2 framing.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
9 / 21

## Slide 10
Phase 2: Strategy
Convert the diagnostic into a set of decisions PetroNusa can commit to.
Approx. 5 months
Phase objectives
A defensible competitive response plan for core fuel retail
A target non-fuel retail proposition, sized and sequenced
A target operating model with phased transition
A unified wallet and loyalty design
An integrated transformation roadmap
Key activities by Objective
Objective A: competitive response plan, network footprint decisions
Objective B: target NFR proposition by archetype, partnership-vs-build decisions
Objective C: target operating model design with phased transition path
Objective D: unified wallet design and loyalty proposition
Objective E: integrated transformation roadmap, governance design
Phase deliverable
Strategy Synthesis Deck plus Integrated Transformation Roadmap, presented at SC5.
Audience: Strategy Committee and Board; separate sessions for operational leadership (Mei-Ling Tan, Pak Yusuf Hadi).
Entry criteria
SC3 sign-off; strategy team mobilised.
Exit criteria
SC5 sign-off of strategy across all five Objectives; commitment to Phase 3 scope and shape.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
10 / 21

## Slide 11
Phase 3: Implementation support
Stand up the programme, support the early waves, and transition execution capability to PetroNusa.
Approx. 10 months
Phase objectives
Pilot the highest-priority moves under each Objective
Establish the programme management infrastructure
Transition execution capability to the PetroNusa Transformation Office
Key activities by Objective
Objective A: pilot pricing architecture and format upgrades on 50–80 sites
Objective B: NFR pilot launch at 30 sites, scale playbook
Objective C: operating model rollout — governance, performance management, technology
Objective D: wallet build oversight, launch readiness
Objective E: Transformation Office stand-up, programme infrastructure
Phase deliverable
Programme close-out pack: Wave 1 read-out, Transformation Office operating handbook, lessons-learned read, presented at SC7.
Audience: Strategy Committee; PetroNusa Transformation Office.
Entry criteria
SC5 sign-off; Transformation Office staffed.
Exit criteria
SC7 sign-off; programme transitioned to PetroNusa Transformation Office.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
11 / 21

## Slide 12
Timeline and Steering Committee cadence
Seven Steering Committees across the engagement, weighted toward direction-setting in Phases 1 and 2.
Diagnostics (~3 months)
Strategy (~5 months)
Implementation support (~10 months)
SC1
SC2
SC3
SC4
SC5
SC6
SC7
Phase | SteerCo | Position | Focus
Diagnostics | SC1 | Start of Phase 1 | Project kickoff, scope confirmation, working-team alignment
Diagnostics | SC2 | Mid-Phase 1 | Diagnostic early findings; emerging hypothesis review
Diagnostics | SC3 | End of Phase 1 | Diagnostics sign-off; framing of Phase 2 strategic choices
Strategy | SC4 | Mid-Phase 2 | Strategic direction across Objectives; trade-off resolution
Strategy | SC5 | End of Phase 2 | Strategy sign-off; Phase 3 commitment
Implementation | SC6 | Mid-Phase 3 | Pilot Wave 1 read-out; mid-course correction
Implementation | SC7 | End of Phase 3 | Programme close; transition to PetroNusa Transformation Office
Three SCs in Diagnostics, two in Strategy, two in Implementation. Cadence is denser early because direction-setting carries higher leverage than execution-phase reviews.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
12 / 21

## Slide 13
Deliverables by phase
Concrete deliverables at the close of each phase, with clear audience and decision purpose.
Phase | Deliverable | Audience | Decision it supports
Diagnostics | Diagnostics Synthesis Deck (~80 slides + appendices), covering all five Objective areas | Strategy Committee, CEO, CFO | Confirm diagnosis; commit to Phase 2 framing
Strategy | Strategy Synthesis Deck plus Integrated Transformation Roadmap (~120 slides total) | Strategy Committee, Board | Commit to strategy across five Objectives; commit to Phase 3 scope
Implementation | Programme close-out pack: Wave 1 read-out, Transformation Office operating handbook, lessons-learned read (~60 slides + ~30-page handbook) | Strategy Committee, Transformation Office | Transition execution capability to PetroNusa; commit to next wave
Interim materials are produced between SteerCos as required — working sessions, hypothesis read-outs, expert interview synthesis.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
13 / 21

## Slide 14
Deliverable example — Objective A (Fuel Retail Competitive Position)
What 'good' looks like for Objective A.
Share-loss waterfall
By region, station archetype, and time period — pinpoints where share has been lost and to whom.
Pricing architecture analysis
Current versus proposed pricing tiers across grades and station archetypes, with margin-impact view.
Network footprint map
Recommended actions per station (invest / hold / divest / convert format) with rationale.
Format upgrade specification
Site-level upgrade kit for the priority site type, with sequencing and capex view.
Indicative format: approx. 30-slide synthesis deck within the Phase 2 strategy deliverable, plus an appendix of station-level analysis.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
14 / 21

## Slide 15
Deliverable example — Objective B (Non-Fuel Retail Build)
What 'good' looks like for Objective B.
Station archetype taxonomy
Clustering of the 620-site network into 4–6 archetypes for which the non-fuel retail proposition will differ.
Category opportunity sizing
By archetype — convenience, food-service, car wash, financial services, etc.
Partnership-vs-build matrix
Recommended approach by category with the reasoning — capability gap, brand fit, capital intensity, time-to-market.
Pilot site selection and operating capability
Site selection for the 30-site Phase 3 launch wave, plus what PetroNusa needs to add (people, processes, systems) to operate the proposition.
Indicative format: approx. 40-slide synthesis deck within the Phase 2 strategy deliverable.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
15 / 21

## Slide 16
Deliverable example — Objective C (Dealer and Estate Operating Model)
What 'good' looks like for Objective C.
Current-state operating model map
Governance, performance management, technology — split company-operated versus dealer-operated estate.
Gap analysis
Where the current model breaks down, with quotes from interviews to anchor the analysis.
Target operating model design
Proposed governance and performance management structure, technology blueprint, dealer commission structure review.
Phased transition plan
What changes in Phase 3, what changes after, with the change-management considerations for the dealer base.
Indicative format: approx. 35-slide synthesis deck within the Phase 2 strategy deliverable, plus a separate dealer-commission technical appendix.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
16 / 21

## Slide 17
Deliverable example — Objective D (Payments and Loyalty)
What 'good' looks like for Objective D.
Current-state assessment
Payments infrastructure, loyalty programme reach, customer data infrastructure.
Benchmark
Domestic and regional comparators across fuel retail wallets; all comparator names anonymised in the final deliverable.
Unified customer wallet design
Proposed wallet architecture covering fuel, NFR, food-service, third-party merchants, with the loyalty mechanic mapped through.
Build-vs-partner choice for the wallet platform
Recommended approach with the reasoning — capability gap, time-to-market, control over the customer relationship.
Indicative format: approx. 25-slide synthesis deck within the Phase 2 strategy deliverable.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
17 / 21

## Slide 18
Deliverable example — Objective E (Transformation Roadmap and Programme Set-up)
What 'good' looks like for Objective E.
Integrated transformation roadmap
Single-page view of the sequencing of moves across Objectives A–D over the implementation horizon, with dependencies and decision points called out.
Wave 1 implementation plan
What gets done in the first nine months of Phase 3, by Objective, with the success criteria.
Transformation Office operating handbook
Governance, decision rights, performance management, escalation paths.
Risk register and mitigation plan
Cross-Objective risks ranked by likelihood and impact, with named mitigation owners.
Indicative format: a board-ready single-page roadmap plus an approx. 30-slide programme handbook.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
18 / 21

## Slide 19
Team and expert bench
A senior Aurelian core team on the ground in Sariwon, supported by a fuel retail expert bench across all five Objectives.
Aurelian core team
Partner
Marcus Whelan
10–15% time
Accountable for the engagement; SteerCo lead.
Principal / Director
One; senior
25–30% time
Workstream architect across all five Objectives.
Engagement Managers
Two
80–100% time each
Workstream clusters: A+D and B+C; E coordinated across.
Consultants and Analysts
Four to five
100% time
Working across all Objectives; on-the-ground delivery.
Local presence
Aurelian Southeast Asia practice
—
Team based in-country for the engagement duration.
Expert bench
Six fuel retail experts curated for the engagement
Spanning competitive strategy, non-fuel retail build, operating model design, and payments and loyalty
Available for diagnostic interviews, hypothesis testing, and SteerCo-level validation throughout Phases 1 and 2
Two further specialist experts from the Aurelian payments and convenience-retail benches can be drawn on for specific working sessions
Named expert profiles on the following slide.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
19 / 21

## Slide 20
Expert bench — named experts proposed for this engagement
Six experts from the Aurelian network, each mapped to one or more of the RFP Objectives.
Expert | Background | Maps to | Engagement mode
Pak Aditya Pratama | Retired Country Head, Royal Pacific Petroleum (Sariwon and the eastern archipelago markets); 25 years Southeast Asian fuel retail; deep experience with state-linked operators; speaks Bahasa Sariwon. | C, E | Diagnostic interviews; SteerCo participation; on-the-ground translation of recommendations.
Sofia Rinaldi | Ex-Managing Director, Corvia Retail Energy; European fuel retail; convenience-led transformation of motorway sites; recognised authority on non-fuel retail build at the station. | B | Diagnostic interviews; non-fuel retail proposition workshop.
Rajeev Khanna | Former Group Head of Retail, Sindhu Fuels; led network rationalisation programme across 14,000 stations across the subcontinent; deep expertise in station economics, dealer commissions, and emerging-market footprint optimisation. | A, C | Network footprint workshop; dealer commission review.
Rina Sundaram | Ex-Head of Non-Fuel Retail, Vasant Petro; built the largest non-fuel proposition in subcontinental fuel retail from 1% revenue contribution to 18% over six years; depth on partnership-versus-build category strategy. | B | Non-fuel retail proposition workshop; partnership-vs-build session.
Marisol Vasquez | Former Head of Retail Marketing, PetroAndina; led the launch of the country's largest fuel-station-based mobile wallet, reaching 8M+ active users; loyalty programme design and payments-enabled propositions. | D | Wallet design session; loyalty proposition workshop.
Dr Ekrem Yıldız | Independent industry economist (national energy markets authority background); widely-cited papers on the long-term margin compression of fuel retail in emerging economies and the timing of EV-driven volume decline. | A, cross-cutting | Diagnostic analytical session; SC-level perspective on EV timing and margin trajectory.
Two additional experts from the Aurelian payments and convenience-retail benches will be drawn on for specific working sessions; full bench available on request.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
20 / 21

## Slide 21
Next steps
What we propose to do in the four weeks before SC1.
1
SoW approval
PetroNusa Strategy Committee reviews and approves the Statement of Work.
2
Engagement letter
Aurelian issues the engagement letter for signature.
3
Team mobilisation
Aurelian core team mobilises in-country; key client counterparts confirmed by PetroNusa (Mei-Ling Tan for operations, Pak Yusuf Hadi for dealer relations, others as needed).
4
Data access
Data access agreed across the five Objective areas; initial data requests issued one week ahead of SC1.
5
SC1 preparation
Working sessions with the PetroNusa team in the week before SC1 to confirm hypotheses and align on diagnostic priorities.
We look forward to working with PetroNusa on this transformation.
Aurelian & Co. — Confidential
PetroNusa SoW — Strategic Transformation of Fuel Retail and Adjacent Businesses
21 / 21