Design Priorities for PetroNusa Unified Wallet

Note from Mei-Ling Tan, Head of Retail Operations  |  Week 5 draft

Internal working note  |  Not for external distribution  |  DRAFT

# 1.  Priority Framing

This is my working list before the P40 kick-off. Not polished - just want the team to have a clear sense of where I stand before we spend three weeks going back and forth on feature lists.

Top priority: FRICTION REDUCTION.

Customers at the pump - especially 2-wheeler riders - have maybe 2-3 minutes. Max. Every extra tap is adoption we lose. Fast-pay has to be the anchor feature, not a nice-to-have.

I've watched the pilot data from the Cempaka Raya corridor. The drop-off at step 3 of the current app flow is >40%. That's not a comms problem, that's a UX problem. Fix the flow first.

Stored value top-up needs to work offline or near-offline. Network coverage at some COCO sites is patchy - don't build something that fails when 4G drops.

On loyalty mechanics:

The wallet should reward fuel-visit behaviour specifically. Points for coffee at a partner convenience chain doesn't keep anyone coming to a PetroNusa station.

I know the digital team will want to open this up to partners eventually. Fine - but that's Phase 2. Phase 1 needs to be about cementing the fuel relationship.

On non-fuel:

Non-fuel has to be first-class in the design - not bolted on as an afterthought. I've been pushing this for two years. Our peer set is at 6-8% non-fuel revenue mix; we're sitting at ~3%. The wallet is the single best lever we have.

Convenience store attachment at the pump (scan-and-pay, pre-order) is the mechanism. If we can cut the friction between 'fill up' and 'grab a drink', basket sizes will follow.

[Pending review by retail ops team - check with Suharti on C-store SKU readiness]

# 2.  Rough M12 Expectations

Flagging upfront: these are MY rough numbers, not the model. The team should run the proper adoption model - I'm just giving a sense check from my experience running the loyalty programme.

My gut feel is maybe 50,000 wallets by M12. I know that sounds conservative but we haven't really done digital loyalty at scale before and I don't want to overpromise to the Board. Happy to be proven wrong by the model.

That 50k figure assumes a cautious rollout - maybe 80-100 COCO sites in Nusakerta Barat and Kertapura. If we get Nusakerta Barat AND Talunagara Tengah COCO sites live by M6, the numbers should be higher.

Again - please use the transaction profile data to model this properly. My number above is informal and I've told Marcus the same. Don't anchor the Board on my gut feel.

TBC: will the M12 target be split into 'registered' vs 'active' users? Important distinction for how we report to the Board. Suggest the team agree a definition before the SteerCo deck.

# 3.  DODO - Keep It Off the Critical Path

DODO is a separate headache. Don't block the COCO launch waiting for DODO to catch up.

The P10 readiness findings were pretty clear - DODO sites have a significant infrastructure gap vs COCO. POS integration, network, hardware - all behind. Pak Yusuf knows this.

DODO franchisees have very different investment appetite to the COCO estate. A number of them are already stretched on the mandated rebranding programme. Asking them to also fund terminal upgrades for the wallet launch is a negotiation that will take months.

My recommendation: DODO should run as a parallel workstream with its own timeline, not a dependency for COCO go-live. 136 sites vs 484 - the maths on where to focus is obvious.

Happy to defend this position at SteerCo if needed. The priority is getting something live for COCO customers by Month 6.

[Note: Pak Yusuf may push back on the framing. Will need to align on comms to DODO network before this goes to SteerCo. - MLT]

# 4.  Feature List - My View

Short and simple. I've seen competitor apps try to launch with 8 features and none of them worked properly at launch. Start with what matters.

Must-have at go-live:

Fast-pay at pump (QR or NFC - TBC on infrastructure read from P10)

Stored value wallet with easy top-up (bank transfer, convenience store)

Basic points for fuel visits (litres or visit-based, simple mechanic)

Convenience store attachment - scan-and-pay at C-store checkout

Nice-to-have (Phase 2 / post-M12):

Partner redemption network (non-fuel merchants)

Tiered status / premium loyalty

In-app fuel price lock or pre-booking

Fleet / SME wallet variant

Things I'm sceptical of:

Complicated tier structures at launch. Keep it simple for the customer. Bronze/Silver/Gold with 12 earn rules is not 'simple'.

Gamification at Phase 1. Not our customer demographic - or at least not proven.

Biometric payment as a go-live requirement. Nice for the press release, not something we can guarantee on our POS estate by M6.

TBC with tech team: which of the Phase 1 features are compatible with the sourcing architecture coming out of P13. Don't want to spec something that the platform can't deliver in time.

# 5.  Non-Negotiables

For the record - things I will push back on hard if the design goes a different direction:

COCO-first launch. Not a simultaneous 620-station rollout. We don't have the operational bandwidth and the risk of a bad first impression is too high.

Go-live at Month 6 is the commitment to the Board. I've already said this publicly. Slipping to Month 9 is not acceptable without a very strong reason.

The wallet must work for 2-wheeler customers. They are the majority of our visit frequency. Any design that implicitly assumes 4-wheel car customers is wrong.

Please circulate to the P40 workstream leads before the Thursday session. I'll be dialling in for the first 30 minutes - Marcus has the full hour.
- MLT, Week 5